## Issues
Issue key | Issue id | Issue Type | Status | Project key | Priority | Resolution | Assignee | Reporter | Created | Updated | Resolved | Due Date | Summary | Custom field (Story Points) | Custom field (Flagged) | Custom field (Sprint added) | Labels | Labels | Parent summary | Custom field (Development started)
BLC-401 | 10000 | Bug | Done | BLC | Highest | Done | Alex Rivera | Dana Wells | 2026-07-22 | 2026-07-22 | 2026-08-05 | 2026-08-07 | Checkout crash on Safari 17 when applying a promo code | 8 |  |  | customer-impact |  | Checkout Stability | 2026-08-03
BLC-402 | 10001 | Story | Done | BLC | High | Done | Priya Nair | Dana Wells | 2026-07-25 | 2026-07-25 | 2026-08-06 | 2026-08-10 | Cart abandonment email — template and send scheduling | 5 |  |  |  |  | Conversion | 2026-08-03
BLC-405 | 10002 | Story | Done | BLC | Medium | Done | Jordan Lee | Dana Wells | 2026-07-28 | 2026-07-28 | 2026-08-07 | 2026-08-11 | Add address autocomplete to the delivery step | 5 |  |  |  |  | Checkout Stability | 2026-08-03
BLC-407 | 10003 | Story | Done | BLC | High | Done | Sam Okafor | Dana Wells | 2026-07-24 | 2026-07-24 | 2026-08-06 | 2026-08-07 | Payment retry logic for declined cards | 5 |  |  |  |  | Payments | 2026-08-03
BLC-416 | 10004 | Bug | In Progress | BLC | Medium |  | Priya Nair | Dana Wells | 2026-07-29 | 2026-07-29 |  | 2026-08-12 | Order confirmation email missing line item tax breakdown | 3 |  |  |  |  | Order Management | 2026-08-06
BLC-418 | 10005 | Bug | Done | BLC | Medium | Done | Alex Rivera | Dana Wells | 2026-07-26 | 2026-07-26 | 2026-08-07 | 2026-08-10 | Guest checkout session expires too early | 3 |  |  |  |  | Checkout Stability | 2026-08-04
BLC-421 | 10006 | Bug | In Review | BLC | High |  | Sam Okafor | Dana Wells | 2026-07-30 | 2026-07-30 |  | 2026-08-11 | Refund webhook occasionally fires twice | 3 | Impediment |  | blocked-external |  | Payments | 2026-08-07
BLC-424 | 10007 | Bug | To Do | BLC | Medium |  | Jordan Lee | Dana Wells | 2026-07-31 | 2026-07-31 |  | 2026-08-13 | Search results ignore the in-stock filter | 3 |  |  |  |  | Catalogue
BLC-429 | 10008 | Bug | In Progress | BLC | Highest |  | Alex Rivera | Dana Wells | 2026-07-20 | 2026-07-20 |  | 2026-08-07 | Inventory sync race condition oversells limited stock | 8 | Impediment |  | customer-impact | blocked-external | Catalogue | 2026-08-04
BLC-433 | 10009 | Story | In Progress | BLC | High |  | Priya Nair | Dana Wells | 2026-07-27 | 2026-07-27 |  | 2026-08-12 | Promo code stacking rules are inconsistent at checkout | 5 |  |  |  |  | Checkout Stability | 2026-08-06
BLC-436 | 10010 | Story | To Do | BLC | High |  | Jordan Lee | Dana Wells | 2026-07-18 | 2026-07-18 |  | 2026-08-10 | Accessibility: checkout form labels not announced by screen readers | 5 |  |  | compliance |  | Checkout Stability
BLC-438 | 10011 | Task | To Do | BLC | High |  | Sam Okafor | Dana Wells | 2026-06-30 | 2026-06-30 |  | 2026-08-14 | Upgrade payment SDK to v9 before deprecation | 5 |  |  | tech-debt |  | Payments
BLC-441 | 10012 | Bug | In Review | BLC | High |  | Sam Okafor | Dana Wells | 2026-08-01 | 2026-08-01 |  | 2026-08-12 | Saved cards not shown for returning customers | 3 | Impediment |  |  |  | Payments | 2026-08-06
BLC-443 | 10013 | Task | To Do | BLC | Low |  | Priya Nair | Dana Wells | 2026-08-02 | 2026-08-02 |  | 2026-08-14 | Analytics events missing on the review-order step | 2 |  |  |  |  | Conversion
BLC-447 | 10014 | Task | Done | BLC | Medium | Done | Jordan Lee | Dana Wells | 2026-08-03 | 2026-08-03 | 2026-08-09 | 2026-08-12 | Fix flaky checkout end-to-end test | 2 |  |  | tech-debt |  | Checkout Stability | 2026-08-08
BLC-450 | 10015 | Task | Done | BLC | Low | Done | Priya Nair | Dana Wells | 2026-08-05 | 2026-08-05 | 2026-08-09 | 2026-08-11 | Update shipping cut-off copy for August bank holiday | 1 |  | Yes |  |  | Order Management | 2026-08-08
BLC-451 | 10016 | Bug | In Progress | BLC | Highest |  | Alex Rivera | Dana Wells | 2026-08-06 | 2026-08-06 |  | 2026-08-11 | Hotfix: gift card balance shows as zero after partial use | 5 |  | Yes | customer-impact | unplanned | Payments | 2026-08-07
BLC-452 | 10017 | Task | Done | BLC | Low | Done | Sam Okafor | Dana Wells | 2026-08-06 | 2026-08-06 | 2026-08-10 | 2026-08-13 | Add server-side logging to the promo service | 2 |  | Yes |  |  | Checkout Stability | 2026-08-09
BLC-453 | 10018 | Task | Done | BLC | Low | Done | Jordan Lee | Dana Wells | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-14 | Copy change: returns policy link in footer | 1 |  | Yes |  |  | Order Management | 2026-08-09
BLC-455 | 10019 | Bug | Done | BLC | Medium | Done | Alex Rivera | Dana Wells | 2026-07-21 | 2026-07-21 | 2026-08-06 | 2026-08-06 | Bulk order CSV import fails over 500 rows | 3 |  |  |  |  | Order Management | 2026-08-04
BLC-458 | 10020 | Bug | Done | BLC | Medium | Done | Priya Nair | Dana Wells | 2026-07-23 | 2026-07-23 | 2026-08-07 | 2026-08-07 | Product image CDN cache invalidation delay | 3 |  |  |  |  | Catalogue | 2026-08-05
BLC-460 | 10021 | Story | Done | BLC | Medium | Done | Sam Okafor | Dana Wells | 2026-07-29 | 2026-07-29 | 2026-08-08 | 2026-08-10 | Wishlist items lost when a guest signs in | 3 |  |  |  |  | Conversion | 2026-08-05